DESERTED ECHOES Sprint 1 Planning Meeting IT8101 Games Development ¦ Group 3 ¦ Meeting Date: April 8, 2026

| Meeting Date April 8, 2026 | Sprint Dates Apr 8 – 14, 2026 | Sprint Theme Foundation & Project Setup | Sprints Left 8 of 8 |
| --- | --- | --- | --- |

1.  Attendance

| # | Full Name | Student ID | Present / Absent |
| --- | --- | --- | --- |
| 1 | Ali Husain Ali Ebrahim Ali Alsaffar (Scrum Master) | 201900576 | Present / Absent |
| 2 | Ali Abdulla | 202300917 | Present / Absent |
| 3 | Faisal Alasfoor | 202304774 | Present / Absent |
| 4 | Habib Husain Alshoofa | 202100747 | Present / Absent |
| 5 | Khizar Azhar | 202200123 | Present / Absent |
| 6 | Rawh Hasan | 202301152 | Present / Absent |

2.  Project Recap

| About the Game Title: Deserted Echoes Genre: 2D Pixel Art — Survival / Exploration / Action Platform: PC (Keyboard + Mouse) Engine: Unity 2D — Universal Render Pipeline (URP) Protagonist: Lucian Blaze (LB) — survivor stranded in a hostile desert World: 12 Levels + Open World Hub (6 tunnels → 12 levels via portals) Duration: 4–6 hours total ¦ 15–25 min per level Game Due: May 24, 2026 ¦ Logbook: May 21 ¦ Viva: May 29 Story Summary Lucian Blaze is stranded in a vast desert after a bandit ambush. His friends were kidnapped and scattered across regions controlled by desert raiders. Players must survive extreme heat, cold, and sandstorms — gathering resources, fighting enemies, and rescuing all friends across 12 levels. | Sprint Status Sprint 1 (Apr 8–14): Foundation — setup, movement, camera, HUD, test level Sprint 2 (Apr 15–21): Combat & Enemy AI — combat, AI, health, death Sprint 3 (Apr 22–28): Survival — day/night, stamina, weather, custom features Sprint 4 (Apr 29–May 5): Inventory, Level Design, Save/Load Sprint 5 (May 6–12): Enemy Variety, Loot, XP System Sprint 6 (May 13–16): Mini-Bosses, Levels 5–10 Sprint 7 (May 17–20): UI Polish, Map, Credits, VFX Sprint 8 (May 21–24): Final Boss, Bug Fixes, Build Export GDD Custom Feature Ownership Ali Abdulla: Dynamic Night Visibility System [ADVANCED] + UI / Settings / Saving Khizar Azhar: Collectible & Equipment System Ali Husain: Teleport / Fast Travel System Faisal Alasfoor: Difficulty System Habib Husain Alshoofa: Player Profile & Inventory System Rawh Hasan: Dynamic Weather System |
| --- | --- |

3.  Assessment & Viva Voce Recap

| Project Marking (35% of Total Course Grade) Game Due: May 24, 2026 ¦ SCRUM Logbook Due: May 21, 2026 Basic Features; 40 marks. Custom Features; 30 marks. SCRUM Practice & Logbook; 30 marks. TOTAL; 100 marks. Basic Requirements (ALL must be in the final game) Main Menu: Start, Instructions, Credits, Settings, Quit Minimum 5 playable levels (we have 12 + Hub) At least 1 animated character (player or AI) Custom camera type (top-down smooth tracking) Appropriate user input (keyboard + mouse) Reward system (XP, gold coins, collectibles) Sound effects, music, environmental audio Special effects: particles, post-processing Exported and tested as a PC build (.exe) Bug-free and fully playable from start to finish Custom: 1 Advanced Feature + 5 Additional Features (6 total — one per member) | Viva Voce Examination — MUST PASS (Individual) Due: May 29, 2026 ¦ FAIL VIVA = FAIL THE ENTIRE COURSE (even with 60%+) Component; Max Marks; Key Expectation. Adequate Body of Work; 9; Significant features implemented, exceeding course standards. Industry Standards; 4; Version control, design patterns, Unity best practices. Clear Contribution; 4; Your work is distinct — no conflict with teammates. Explanation of Features; 8; Comprehensive understanding, clear detailed explanations. Teamwork; 5; Proactive collaboration, supporting teammates. TOTAL; 30. Viva Prep — Every Member Must: Know every line of code you wrote — tutors will ask in detail Be ready to demo YOUR specific features live in the Unity editor Speak individually about your OWN contributions only Your Trello cards must exactly match what you coded Update Sprint Logbook every sprint — tutors check this Every feature you build = something you must explain in the Viva |
| --- | --- |

4.  Sprint 1 — Task Distribution

Sprint 1 ¦ April 8 – 14, 2026 ¦ Theme: Foundation & Project Setup Goal: Get a playable skeleton running: player moves in all directions, camera follows, HUD is visible, AudioManager is live, and all 6 members are contributing on Git.

| Member | GDD Feature | Sprint Tasks — What Exactly Needs to Be Built | Est. | Status |
| --- | --- | --- | --- | --- |
| Ali Husain 201900576 (Scrum Master) | Project Setup & Architecture | Unity 2D (URP) project creation — 1920x1080, stable LTS version Folder structure: Scripts, Scenes, Prefabs, Sprites, Animations, UI, Audio, ScriptableObjects, Materials, Tilemaps Git repo setup — main & develop branches + Unity .gitignore CONVENTIONS.md — naming rules (PascalCase files, camelCase vars) Import packages: TextMeshPro, Cinemachine, New Input System, 2D Lights Create all 14 empty scenes and add to Build Settings GameManager.cs singleton (DontDestroyOnLoad) — currentLevel, playerLives SceneLoader.cs static utility — LoadScene(string name) Trello Sprint 1 cards: assign names, due dates, descriptions | ~7.5h | To Do |
| Ali Abdulla 202300917 | Player Movement + Input System | New Input System asset (PlayerInputActions.inputactions) Action Map "Gameplay": Move (2D Vector/WASD), Sprint (Shift), Dodge (Space), Interact (E), Attack (Left Click), Inventory (Tab), Pause (ESC) Player prefab: Rigidbody2D (gravity=0, freeze Z), Capsule Collider 2D PlayerMovement.cs — normalized 8-dir input → rb.linearVelocity Sprint mechanic: Shift → moveSpeed × sprintMultiplier (1.6f) reads currentStamina stub from PlayerStats to gate sprint Sprite flip on movement direction (sr.flipX on horizontal) Collision test: player cannot pass through wall colliders | ~6.5h | To Do |
| Faisal Alasfoor 202304774 | Main Menu UI + HUD Framework | Main Menu Canvas (Screen Space Overlay, 1920x1080, Scale With Screen) "DESERTED ECHOES" TMP title — gold color, size 80, text shadow 5 TMP buttons: Start Game, Instructions, Credits, Settings, Quit Button wiring: Start→SceneLoader, Quit→Application.Quit, others→placeholder panels ("Coming soon") HUD Canvas in test level: health bar (slider, red fill), stamina bar (slider, green fill), gold icon + TMP "0", lives "♥ 3" All HUD elements anchored correctly for multi-resolution Game Over scene: "GAME OVER" heading, Retry + Main Menu buttons UI Style Guide note (colors, font, sizes) in code comment header | ~7.5h | To Do |
| Habib Husain 202100747 | Player Sprite, Animator & Stats | Import player sprite sheet — Texture Type: Sprite 2D, Mode: Multiple, PPU: 32, Filter: Point, Compression: None Sprite Editor: slice into frames (auto-grid by cell size) Create 6 animation clips in Assets/Animations/Player/: Idle (loop), Walk (loop), Run (loop), Attack (no loop), Hurt (no loop), Death (no loop) Animator Controller: transitions driven by float "speed", triggers: Attack, Hurt, Die. Any State → Death. PlayerAnimationController.cs: reads moveSpeed → sets "speed" float public methods: TriggerAttack(), TriggerHurt(), TriggerDeath() Player prefab assembly: all components assigned in Inspector PlayerStats.cs stub: maxHealth=100, currentHealth=100, maxStamina=100, currentStamina=100 | ~9h | To Do |
| Khizar Azhar 202200123 | Camera System + Collectible Prototype | Cinemachine Virtual Camera: Follow=Player, Body=Framing Transposer Damping X/Y = 0.5, Dead Zone = 0, Ortho Size = 6 (test + tune) CinemachineConfiner2D with level boundary composite collider ICollectible.cs interface: void Collect(GameObject collector) Collectible.cs: OnTriggerEnter2D → if Player tag → Collect() → Destroy CoinCollectible prefab: circle sprite (yellow), CircleCollider2D (IsTrigger) 5 coin collectibles placed in test level Camera follow verification: smooth, no jitter, stays within bounds | ~5h | To Do |
| Rawh Hasan 202301152 | Test Level + AudioManager | Level_01 scene (or TestLevel): tilemap or sprite floor ~30×20 units Perimeter walls: Box Collider 2D invisible walls (Layer: Ground) 3-4 internal obstacles (rocks/boxes) for navigation variety SpawnPoint empty GameObject — center-left of level LevelManager.cs: Instantiate(PlayerPrefab, spawnPoint.position) on Start() Global Light 2D (URP 2D lighting) — Intensity 1.0, warm white Basic desert environment props (colored sprites for atmosphere) AudioManager.cs singleton (DontDestroyOnLoad): 2 AudioSources (music loop, SFX one-shot) PlayMusic(clip), PlaySFX(clip), SetMusicVolume(f), SetSFXVolume(f) Volumes saved to PlayerPrefs Placeholder audio clips imported (wind loop, coin pickup chime) | ~8.5h | To Do |

5.  Integration Points & Definition of Done

| Sprint 1 — System Integration Map From (Provider); To (Consumer); What to Share / How. Ali Husain (SceneLoader); Faisal (Menu Buttons); SceneLoader.LoadScene() wired to Start button OnClick. Ali Husain (GameManager); All members; Singleton: GameManager.Instance from any script. Habib (PlayerPrefab); Ali Abdulla (Movement); PlayerMovement.cs attached to same prefab. Habib (PlayerStats stub); Ali Abdulla (Sprint); PlayerMovement reads PlayerStats.currentStamina. Rawh (LevelManager); Habib (PlayerPrefab); PlayerPrefab assigned in LevelManager Inspector field. Khizar (Cinemachine); Rawh (SpawnPoint); Camera Follow target = player instantiated by LevelManager. Rawh (AudioManager); All members; AudioManager.Instance.PlaySFX(clip) callable from anywhere. | Sprint 1 — Definition of Done A task is only DONE when ALL of these apply: Unity project committed to Git — all 6 members made at least 1 push Folder structure is clean — no loose files outside their folders Player moves in all 8 directions with WASD, sprints with Shift Player sprite flips correctly based on movement direction Walk / Run / Idle animations transition correctly in play mode Cinemachine camera follows the player smoothly with no jitter Main Menu loads with all 5 buttons functional (or showing placeholder) HUD Canvas shows health bar, stamina bar, gold counter, lives AudioManager exists — PlaySFX() callable without errors 5 coin collectibles in level disappear when player touches them All Trello Sprint 1 cards updated with End-of-Sprint results Sprint 1 log filled in the logbook sheet by each member Sprint Rules (Every Sprint) Commit to Git DAILY on the develop branch Assign your name to Trello cards BEFORE starting Fill in Sprint Logbook entry for this week Never modify another member's scene without notice Raise blockers IMMEDIATELY in the group chat Every line you write = something to defend in Viva |
| --- | --- |

Deserted Echoes  |  Group 3  |  IT8101 Games Development  |  Sprint 1: April 8 – 14, 2026  |  Meeting Date: April 8, 2026  |  Prepared by: Ali Husain (Scrum Master)